**Maths Action Plan**

|  |
| --- |
| **ACTION PLAN** |
| **Key Improvement Priority:** **Priority 1- Review teaching and learning of the subject and establish subject knowledge of teachers and any CPD needed****Priority 2 – Collect samples of work from all classes to monitor impact and attainment.****Priority 3 – Understand how are disadvantaged and low attaining pupils performing in relation to their peers?****Priority 4 – Know how character being developed through Maths****Priority 5 – Maths curriculum delivered across the school with clear progression throughout the school using Whiterose scheme and mental maths.** **Priority 6 – use of 3 assessments across the year to inform progress and future planning** | **Year****2023-2024****Review Date****September 2024** | **Lead person accountable for the plan: Mr Taylor** |
| **Focus on outcomes. Specific, measurable impact on pupils.**  | * Children to be aware of the impact of Mathematics.
* Use of mental maths and timetable practice throughout the school.
* Maths curriculum to be delivered across the school with clear progression throughout the school using Whiterose scheme and mental maths.
* Monitor the subject knowledge of both staff and children
* Complete pupil voice on Maths to learn the children’s views on Maths.
 |
| **Intent** | **Implementation – how will it be done** | **Time Scale****Start and End dates** | **Training/CPD****needs** | **Resources/Costs/Time** |
| Review teaching and learning of the subject and establish subject knowledge of teachers and any CPD needed | Lesson observations, pupil voice, staff meetings | Sept 2023- July 2024 | CPD  | CPD |
| Collect samples of work from all classes to monitor impact and attainment.  | Book looks to be carried out each term | Sept 2023- July 2024 |  | Curriculum time to collate. |
| Understand how are disadvantaged and low attaining pupils performing in relation to their peers? | Subject team to carry out book look and pupil voice of those from disadvantage backgrounds/low attainers | Sept 2023- July 2024 | CPD in supporting children | Curriculum time to collate. Teacher time |
| Know how character is being developed through Maths | Monitor planning, and teaching of vocabulary to see impact of character within History | Sept 2023- July 2024 |  | Character passports. Printing vocab |
| Maths curriculum to be delivered across the school with clear progression throughout the school using Whiterose scheme and mental maths. | Ensure staff are aware of resources available. Conduct observations and reviews of Mental maths | Sept 2023- July 2024 | Inset | Cost of new Mental maths books. Whiterose scheme |
| Use of 3 assessments across the year to inform progress and future planning | Observations and gap analysis | Sept 2023- July 2024 | Staff meetings |  |
| IMPACT / Assessment and monitoring  |
| **Who** | **What** | **Where** | **When** | **How** | **External Validation** |
| *All teaching Staff* | *Coverage of History* | *Whole School* | *Each term collect samples of work from each class.*  | *Communicate with other members of staff and collate into a folder.*  | *Share findings and discuss at staff meeting (include subject governor in this)* |
|  |  |  |  |  |  |
| ***Evaluation against success criteria.***  |